## todos
task_id | description | priority | start_date | end_date | station | type | assignee | comments | status
1 | upgrade EPRoC PC, 2TB SSD | medium | 2023-07-24 | 2023-07-30 | EPRoC | maintenance | LR |  | done
2 | order and distribute SSD drives for backup | high | 2023-07-18 | 2023-07-30 | lab | purchase | LR |  | done
3 | clean the cooling system of solid state RF amp | high | 2023-08-01 | 2023-08-02 | X3 | repair | ER, LR |  | done
4 | order 12T magnet maintenance | high | 2023-08-07 | 2023-08-08 | HZB | maintenance | LR, NK |  | done
5 | order 6T magnet maintenance | high | 2023-08-07 | 2023-08-08 | W1 | maintenance | LR |  | done
6 | order turbo pump for Nikolai | high | 2023-08-07 | 2023-08-08 | HZB | purchase | LR, NK |  | done
7 | order EPR tubes, 3.8mm, 1.6mm | high | 2023-08-07 | 2023-08-21 | lab | glassblower | LR |  | done
8 | refill sample storages | medium | 2023-08-21 | 2023-08-22 | lab | maintenance | LR |  | done
9 | fix LOGS data representation issue | high | 2023-08-01 | 2023-08-22 | lab | software | JJ, LR |  | done
10 | order Methyl Viologen | medium | 2023-08-24 | 2023-08-25 | EPRoC | purchase | LR |  | done
11 | upgrade the IF switching on W1 bridge | medium | 2023-07-24 | 2023-08-30 | W1 | Q-band on W1 | LR |  | wip
12 | checking the old insert tube for leaks | medium | 2023-07-17 | 2023-09-05 | W1 | Q-band on W1 | LR |  | wip
13 | checking new insert tube for leaks | medium | 2023-07-18 | 2023-09-06 | W1 | Q-band on W1 | LR |  | wip
14 | upgrade Matlab on EPRoC PC | medium | 2023-09-01 | 2023-09-07 | EPRoC | software | LR |  | done
15 | upgrade Matlab on X3 | medium | 2023-09-01 | 2023-09-07 | X3 | software | LR | reinstall needed, permissions problem | wip
16 | building table extension for W1Q | medium | 2023-07-20 | 2023-09-08 | W1 | Q-band on W1 | LR |  | wip
17 | request additional cooling system on Q3 stage | high | 2023-08-16 | 2023-09-10 | Q3 | Inst. Dienst | LR, ID |  | done
18 | bug fixes on EPR Simulator, all OS types | high | 2023-09-01 | 2023-09-11 | lab | software | LR |  | done
19 | order 'raaco' organizers for ED | medium | 2023-08-14 | 2023-09-15 | lab | inventory | LR, ER |  | done
20 | order glassware for EPR tubes | high | 2023-08-23 | 2023-09-20 | lab | purchase | LR |  | done
21 | get quotation on Quad Det CW | medium | 2023-08-20 | 2023-09-20 | W1 | purchase | LR |  | pending
22 | new coworker: Anna Scott | high | 2023-09-27 | 2023-09-29 | lab | personel | LR |  | done
23 | order He5.0 for compressor maintenance | medium | 2023-08-24 | 2023-09-30 | W1 | maintenance | LR |  | done
24 | get an offer from Bruker MT dewar, part #4104 | high | 2023-10-06 | 2023-10-06 | MT | repair | LR |  | done
25 | check if oxford cryostat fits to MT | high | 2023-10-09 | 2023-10-09 | MT | maintenance | LR | it fits, needs an adapter | done
26 | get an offer on Oxford cryos 45 and 90 degree | high | 2023-10-09 | 2023-10-13 | MT | upgrade | LR |  | done
27 | get an offer on MT he cryos 45 | high | 2023-10-09 | 2023-10-13 | MT | upgrade | LR | doesn't exist | done
28 | X3 Q-band extension box, fan is not working, unstable phase | high | 2023-10-20 | 2023-10-20 | X3 | repair | LR | seems to be working fine | done
29 | get the repair number from Bruker, X3 mod ampm SPU | high | 2023-10-20 | 2023-10-23 | X3 | repair | LR |  | done
30 | finish PSII story | high | 2023-09-01 | 2023-10-31 | lab | writing | LR | DONE! | done
31 | report to Einkauf that they can pay HZB magnet maintenance | high | 2023-10-17 | 2023-11-01 | HZB | maintenance | LR |  | done
32 | set up an appointment with Cryogenic | high | 2023-09-27 | 2023-11-03 | W1 | maintenance | LR | call Sam on Thursday 2.11.23 | done
33 | measure background on W1 | high | 2023-11-06 | 2023-11-06 | W1 | maintenance | LR | res = needs cleaning, strong BG | done
34 | reprint the EC cell for Kaltum | high | 2023-11-06 | 2023-11-07 | lab | 3D printing | LR | order new materials | done
35 | order ESR5000 VT cryo tube | high | 2023-11-01 | 2023-11-08 | MT | purchase | LR |  | done
36 | arrange the 400 MHz RF amp for X3 | high | 2023-11-14 | 2023-11-14 | X3 | setup | LR | Mn ENDOR needed, TL project | done
37 | check issues with Rf amp on X3 | high | 2023-10-16 | 2023-11-15 | X3 | repair | LR | cleaned the filter, the flow is normal | done
38 | order compatible with MT finger dewar | high | 2023-11-14 | 2023-11-16 | MT | purchase | LR | request an offer again, there was no "magic" line in request | wip
39 | buy Swagelok valve and 0.5 bar pressure release valve | high | 2023-11-13 | 2023-11-17 | W1 | upgrade | LR | switch for sample changing optimization | pending
40 | checking for leaks in BAC4 | medium | 2023-11-08 | 2023-12-28 | W1 | Q-band on W1 | LR |  | wip
41 | order resins and filaments for 3D printing | medium | 2023-11-06 | 2023-11-20 | lab | 3D printing | LR | tough 1500, rigid 10K, elastic 80A | pending
42 | update the labstep-LOGS script | high | 2023-10-09 | 2023-11-30 | lab | software | JJ, LR | not working as intended | wip
43 | order some vacuum adapters and clams | high | 2023-10-31 | 2023-11-30 | lab | purchase | LR |  | pending
44 | improve the sample loading procedure - pump-purge switch | low | 2023-07-24 | 2023-12-31 | W1 | W1 optimisation | LR | need vacuum parts and swagelock valve | wip
45 | install Matlab on W1 | low | 2023-12-01 | 2023-12-31 | W1 | upgrade | LR | needs a newer OS | pending
46 | update OS on W1 | low | 2023-12-01 | 2023-12-31 | W1 | upgrade | LR | require spectrometer downtime | pending
47 | bug fixes on EPR Simulator, all OS types (feedback after school/Exp parameters) | low | 2023-11-01 | 2023-12-31 | lab | software | LR |  | pending
48 | redesign the EC cell for better printability/manufacturing | medium | 2023-11-14 | 2023-12-31 | leb | 3D printing | LR |  | pending
Formulas:
end_date = Table5[[#This Row],[start_date]]+1
start_date = [start_date, row above]+1
start_date = [start_date, row below]+2
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.